## Figure 1.1
Size of overrun |  | Proportion of projects | Proportion of the value of overruns
Underun | ≤ 25% | 9.2251 | -8.5762
On budget | 0 | 56.6421 | 0
Overrun | ≤ 25% | 11.2546 | 5.8292
Overrun | 25% - 50% | 5.7196 | 3.8956
Overrun | > 50% | 17.1587 | 90.2752

## Figure 1.2
Study | Sample size
Victorian Auditor General 2010 | 7
Duffield et al. 2008 | 23
Wood 2010 | 46
NSW Auditor General 2015 | 50
Love et al. 2012 | 62
Grattan Institute 2016 | 542

## Figure 1.4
Cost overruns, as a per cent of initial project cost
| Lower bound | Upper bound
First public cost announcement | 0 | 0
Formal funding commitment | 8.86 | 19.36
Commencement of construction | 15.25 | 31.98
Project completion | 24.4 | 42.45

## Figure 1.5
Per cent of cost overruns attributable to each cause
Scope changes | 0.11359
Other/unknown | 0.88641

## Figure 2.1
| Possible or under consideration | Committed | Under construction
Percentage of projects | 32.4723 | 26.1993 | 41.3284
Percentage of the cost of cost overruns | 74.2976 | 6.5845 | 19.1178

## Figure 2.2
Average project size when | Possible or under consideration | Committed | Under construction
First possible or under consideration | 225.6174 | 208.3205 | 196.478
First committed | 282.5844 | 208.3833 | 196.478
First under construction | 311.7379 | 223.2769 | 196.478
Completed | 342.3009 | 221.1374 | 220.0686

## Figure 2.3
Date | Estimated cost, $m
2001 | 136
2005-05-01 | 337
2005-08-01 | 370
2006 | 511
2007 | 631
2009 | 705
Final | 688

## Figure 2.4
| Not on IA priority list | Yet to be assessed for IA priority list | On IA priority list
Greens | 46.01% | 53.99% | 0%
Labor | 34.13% | 62.87% | 3.005%
Coalition | 25.56% | 59.86% | 14.58%

## Figure 2.5
Date | Estimated cost, $m
2003 | 593.5
2007 | 1100
2008 | 1950
Final | 1755

## Figure 3.1
Average magnitude of cost overruns
Prior to a formal funding commitment | 0.08857
Budget commitment – under construction | 0.063953
During construction | 0.091434
Overall | 0.24396

## Figure 3.2
Date | Estimated cost, $m
2002 | 350
2007 | 887
2008 | 1700
2009 | 1700
Final | 1700

## Figure 3.3
Cancellation rate across all projects by project stage
At the end of the "under consideration" stage | 28.15%
At the end of the "committed" stage | 14.83%
At the end of the "under construction" stage | 13.67% | s

## Figure 4.1
| Underrun | On budget | Overrun
Assumed | 25% | 50% | 25%
Observed | 9.225% | 56.64% | 34.13%

## Figure 4.2
| Less than 300m | 300m-600m | Greater than 600m
Prevalence of overruns | 30.61% | 46.67% | 53.66%
Mean overrun as proportion of initial project size | 0.23153 | 0.32526 | 0.54178

## Figure 4.3
Average magnitude of overruns, as a proportion of initial project costs
| First announced - contracted | Contracted - completed | Overall
Road | 19.69% | 9.618% | 29.31%
Rail | 8.11% | 8.38% | 16.49%
All | 15.25% | 9.143% | 24.4%

## Figure 4.4
Percentage of guidelines which provide advice on risk measurement that recommend:
Expected value | 58.06%
Probability pricing | 45.16%
Sensitivity analysis | 45.16%
Reference class forecasting | 19.35%

## Figure 5.1
Size of contingency, as a per cent of budgeted costs, required for 90% confidence:
At the portfolio level | 70%
At the project level | 24%

## Figure A.6
Recommended contingency margins, as a per cent of project costs
| QLD |  | AACE |  | SA |  | NGTSM
| Upper bound | Lower bound | Upper bound | Lower bound | Upper bound | Lower bound | Upper bound | Lower bound
Early stage contingency ranges | 70% | 40% | 100% | 30% | 70% | 40% | 25% | 15%
Late stage contingency ranges | 20% | 10% | 15% | 3% | 40% | 0% | 10% | 5%

## Figure B.1
Comparison of the magnitude of cost estimates - only those with a Grattan cost estimate
Investment Monitor ($m) |  | Grattan Dataset ($m)
First cost when possible or under consideration | 3520 | Initial funding commitment | 3664.6
First cost when committed | 8780 | Final funding commitment | 6544.4
First cost when under construction | 14106 | Initial contracted cost | 12741.2
Final cost | 14357 | Actual cost | 14210.6

## Figure B.2
Cost overruns, as a per cent of initial project costs
Investment Monitor dataset | Average magnitude of cost overruns
Initial announcement - funding commitment | 8.857%
Funding commitment - contract | 6.395%
Contract - completion | 9.143%
Initial announcement - completion | 24.4%
Grattan dataset
Initial announcement - funding commitment | 6.497%
Funding commitment - contract | 26.15%
Contract - completion | 19.32%
Initial announcement - completion | 51.97%